## Basic Contact Info
DESCRIPTION:
Project / Application
Event Description
Event Coordinator
Project Manager
Responsible
Activity Date
Start Time |  | End Time:
Risk
Impact
Associated Ticket
Outage Message
Phone Bridge:
CONTACTS:
Contact | Resource Name | E-mail | Pager | Alpha Page | Cell | Phone
Misc
Dept Help Desk |  |  |  | pmcsosoncall@mcis.washington.edu |  | (206) 543-7012, #6
Teleconference Bridge
Security / HVAC Engineering-on-call | [5 empty] | Security will contact the on-call engineer
VALIDATION PLAN:
Product | Resource Name | Subcomponent | Responsible |  | Pass (Y or N) | Comments
<name>
<name>
<name>
<name>
<name>
<name>
<name>
<name>
<name>
<name>
CONTINGENCY PLAN:
Contingency |  |  | Action |  |  | Approval Required
Running beyond Downtime Window
Running > 30 minutes Beyond Downtime Window

## Event Plan
| Group # Cutover Date |  |  | Insert Cutover date to calculate timeline: |  |  |  | 2017-11-03
Ref # | Task | Timing | # Days | Start Date | Time | Duration | # Days | Due | Status | Assigned | Bug | SDM | Notes
Prep Activities
Go No-Go Decision
1 | [8 empty] | Not Started
2 | [8 empty] | Not Started
Change Control
1 | Create ticket for Change Control | t-1w | 7 |  |  |  |  | 2017-10-27 | Not Started
2 | Prior to noon, submit ticket for Change Control | t-1w | 7 |  |  |  |  | 2017-10-27 | Not Started | PM |  |  | Change "CAB" field to "Change Control"
3 | Change Control | t-2d | 14 |  |  |  |  | 2017-10-20 | Not Started | PM |  |  | Present change at weekly meeting
Go-live Tasks
Pre Go-live Tasks
1 | Work with project liaisons to determine owners of shared NetID accounts | t - 2w | 14 | 2017-09-08 |  | 6w | 42 | 2017-10-20 | Not Started | PM/Analyst
2 | Submit request to create endorsement groups for shared NetID accounts | t - 2w | 14 | 2017-10-20 |  | 1d | 0 | 2017-10-20 | Not Started | PM/Analyst |  |  | One endorsement group per owner ("membership manager")
3 | Work with resource owners to settle new names & config parameters for resources to be migrated (if applicable). | t - 1w | 7 | 2017-09-15 |  | 6w | 42 | 2017-10-27 | Not Started | Dept. Help Desk
4 | Create UW groups needed to protect shared resources for this migration group, with Dept. Help Desk as owner | t - 1w | 7 | 2017-09-15 |  | 6w | 42 | 2017-10-27 | Not Started | Dept. Help Desk |  |  | Will be created as resource requirements are settled with owners.
Go-live Tasks
1 | Send final listing of users to be migrated, request migration begin. Also include summary & count of resources to be migrated. To: Comparex cc: Project team, UW-IT PM, Dept. Help Desk | t - 2w | 14 | 2017-10-20 |  | 1d | 0 | 2017-10-20 | Not Started | Analyst |  |  | to UW IT, TSO team
2 | Begin copy of user data from Deskmail to O365 Exchange Online | t - 2w | 0 | 2017-10-23 |  | 1d | 11 | 2017-11-03 | Not Started | Comparex
3 | (Data is copying) |  | 0 | 2017-10-23 |  | 11 days | 11 | 2017-11-03 |  |  |  |  | likely will start later, won't take the full period
4 | Send list of resources to be created, request creation in Exchange Online To: UW-IT Service Center (help@uw.edu), UW-IT PM | t - 1w | 7 | 2017-10-27 |  | 1d | 0 | 2017-10-27 | Not Started | Dept. Help Desk or PM
5 | Create new resources in Exchange Online environment | t-1d | 1 | 2017-11-02 |  | 1d | 0 | 2017-11-02 | Not Started | UW IT |  |  | By EOD Thursday prior to mig. weekend
6 | Notify team when copy of user data & resources is complete | t-1d | 1 | TBD |  | 1d |  | 2017-11-02 | Not Started | Comparex
7 | Send final email to migration group users | cutover | 0 | 2017-11-03 | 16:45 | 1d | 0 | 2017-11-03 | Not Started | PM |  |  | will be last email in Deskmail mailbox
8 | Send email to team to confirm start of migration - change forwarding for Deskmail | cutover | 0 | 2017-11-03 | 17:00 | :05 | 0 | 2017-11-03 | Not Started | PM
9 | Change forwarding of Deskmail accounts | cutover | 0 | 2017-11-03 | 17:00 | :10 | 0 | 2017-11-03 | Not Started | Comparex
10 | Complete switch-over and final sync of email and resources | cutover | 1 | 2017-11-04 | 17:15 |  | 0 | 2017-11-04 | Not Started | Comparex |  |  | catch-up, complete
11 | Notify project team when migration tasks are complete | t+ | 1 | 2017-11-04 |  | 1d | 0 | 2017-11-04 | Not Started | Comparex |  |  | completed Sat. morning, 6/3 @ 6:12 AM
12 | Send exception report of migrated accounts | t+ | 1 | 2017-11-04 |  | 1d | 0 | 2017-11-04 | Not Started | Comparex
13 | Send notification that migration has completed | Go-live | 3 | 2017-11-06 | 6:00 | 1d | 0 | 2017-11-06 | Not Started | PM |  |  | agreed earliest time for EDS support
14
Post Go-live Activities
1 | Grant permissions to shared resources | t+ | 7 | 2017-11-06 |  | 5d | 4 | 2017-11-10 |  | Users |  |  | add users to new groups
2 | Import contacts | t+ | 7 | 2017-11-06 |  | 5d | 4 | 2017-11-10 |  | Users
3 | Provide deskside support to migrated users, as needed | t+ | 7 | 2017-11-06 | 6:00 | 5d | 4 | 2017-11-10 |  | Dept. help staff
4 | Add to group to begin clock for removal of Deskmail account | t+2w | 31 | 2017-11-20 |  | 2w | 14 | 2017-12-04 |  | UW-IT
5 | Notify meeting organizers to update their meetings with new resources
Formulas:
Start Date = [Due]-H13

## Pre-downtime checklist
Area
Description | N/A | Who | Due | Completed
EXAMPLE: Create Change Control Ticket | 0 | BP | 2010-10-14 | 2010-10-14
** Send downtime notification to Help Desk via Help Desk downtime form: http://home.mcis.washington.edu/amcis/helpdesk/downtime.asp