## Summary Date Tracker
|  |  |  | Email L1 |  |  | Email L2+S1 |  |  | Email L3+S2 | Email L4+S3 | Email S4? Dates off? | ? | ? | Email L5? | Email S5 | Email S6?
Group Num | Monday Go-Live Date | Friday Begin Conversion Date | Initial Comm. to Directors | Initial Comm. to Project Liaisons | Schedule Kick-off Meeting | Execute Kick-Off Meeting | Forward draft email for staff and staff presentation template | Schedule 4 weeks Prior Meeting | Execute 4 Weeks Prior meeting | Forward draft email for staff on Migration Prep | Forward draft template for flyers and reminder email | IT send email to accounts being converted | IT sends reminder email to accounts being converted (skip?) | Post Migration Email Draft Sent | Final Conversion Tips for Project Liaisons | IT send email saying email converted to old email location
|  |  | 13 weeks prior | 11-12 weeks prior | 11 weeks prior | 8 weeks prior | 7-8 weeks prior | 7 weeks prior | 4 weeks prior | 3-4 weeks prior | 2 weeks prior | delay to 1 WEEK PRIOR | 2 days prior | 1-2 Days Prior | 1-2 Days Prior | End of Day Friday | 4 DAYS AFTER?
1 | 2017-12-04 | 2017-12-01 | 2017-09-01 | 2017-09-11 12:00 | 2017-09-15 | 2017-10-06 | 2017-10-10 21:36 | 2017-10-13 | 2017-11-03 | 2017-11-06 12:00 | 2017-11-17 | 2017-11-17 | 2017-11-29 | 2017-06-01 | 2017-06-01 | 2017-12-01
2 | 2017-12-11 | 2017-12-08 | 2017-09-08 | 2017-09-18 12:00 | 2017-09-22 | 2017-10-13 | 2017-10-17 21:36 | 2017-10-20 | 2017-11-10 | 2017-11-13 12:00 | 2017-11-24 | 2017-11-24 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-08
3 | 2017-12-18 | 2017-12-15 | 2017-09-15 | 2017-09-25 12:00 | 2017-09-29 | 2017-05-31 | 2017-06-07 | 2017-10-27 | 2017-11-17 | 2017-11-20 12:00 | 2017-12-01 | 2017-12-01 | 2017-12-13 | 2017-12-12 | 2017-12-13 | 2017-12-15
4 | 2018-01-08 | 2018-01-05 | 2017-10-06 | 2017-10-16 12:00 | 2017-10-20 | 2017-11-10 | 2017-06-07 | 2017-11-17 | 2017-12-08 | 2017-12-11 12:00 | 2017-12-22 | 2017-12-22 | 2018-01-03 | 2018-01-02 | 2018-01-03 | 2018-01-05
5 | 2018-01-15 | 2018-01-12 | 2017-10-13 | 2017-10-23 12:00 | 2017-10-27 | 2017-11-17 | 2017-11-21 21:36 | 2017-11-24 | 2017-12-15 | 2017-12-18 12:00 | 2017-12-29 | 2017-12-29 | 2018-01-10 | 2018-01-09 | 2018-01-10 | 2018-01-12
6 | 2018-01-22 | 2018-01-19 | 2017-10-20 | 2017-10-30 12:00 | 2017-11-03 | 2017-11-24 | 2017-11-28 21:36 | 2017-12-01 | 2017-12-22 | 2017-12-25 12:00 | 2018-01-05 | 2018-01-12 | 2018-01-17 | 2018-01-16 | 2018-01-17 | 2018-01-19
7 | 2018-01-29 | 2018-01-26 | 2017-10-27 | 2017-11-06 12:00 | 2017-11-10 | 2017-12-01 | 2017-12-05 21:36 | 2017-12-08 | 2017-12-29 | 2018-01-01 12:00 | 2018-01-12 | 2018-01-19 | 2018-01-24 | 2018-01-23 | 2018-01-24 | 2018-01-26
8 | 2018-02-05 | 2018-02-02 | 2017-11-03 | 2017-11-13 12:00 | 2017-11-17 | 2017-12-08 | 2017-12-12 21:36 | 2017-12-15 | 2018-01-05 | 2018-01-08 12:00 | 2018-01-19 | 2018-01-26 | 2018-01-31 | 2018-01-30 | 2018-01-31 | 2018-02-02
9 | 2018-02-12 | 2018-02-09 | 2017-11-10 | 2017-11-20 12:00 | 2017-11-24 | 2017-12-15 | 2017-12-19 21:36 | 2017-12-22 | 2018-01-12 | 2018-01-15 12:00 | 2018-01-26 | 2018-02-02 | 2018-02-07 | 2018-02-06 | 2018-02-07 | 2018-02-09
10 | 2018-02-19 | 2018-02-16 | 2017-11-17 | 2017-11-27 12:00 | 2017-12-01 | 2017-12-22 | 2017-12-26 21:36 | 2017-12-29 | 2018-01-19 | 2018-01-22 12:00 | 2018-02-02 | 2018-02-09 | 2018-02-14 | 2018-02-13 | 2018-02-14 | 2018-02-16
11 | 2018-02-26 | 2018-02-23 | 2017-11-24 | 2017-12-04 12:00 | 2017-12-08 | 2017-12-29 | 2018-01-02 21:36 | 2018-01-05 | 2018-01-26 | 2018-01-29 12:00 | 2018-02-09 | 2018-02-16 | 2018-02-21 | 2018-02-20 | 2018-02-21 | 2018-02-23
12 | 2018-03-05 | 2018-03-02 | 2017-12-01 | 2017-12-11 12:00 | 2017-12-15 | 2018-01-05 | 2018-01-09 21:36 | 2018-01-12 | 2018-02-02 | 2018-02-05 12:00 | 2018-02-16 | 2018-02-23 | 2018-02-28 | 2018-02-27 | 2018-02-28 | 2018-03-02
|  |  |  | Email L1 |  |  | Email L2+S1 |  |  | Email L3+S2 | Email L4+S3 | Email S4? Dates off? | ? | ? | Email L5? | Email S5 | Email S6?
Need to adjust formula
|  | Email Count | #1 | #2 | #3 | #4 | #5 | #6 | #7 | #8 | #9 | #10 |  | #11
|  |  | Email L1 | Email L2 | Email S1 | Email L3 | Email S2 | Email L4 | Email S3 | Email S4 | Email L5 | Email S5 | Target | Email L6
|  |  | 0365 to Liaisons | 0365 to Liaisons | Liaison to Staff | 0365 to Liaisons | Liaison to Staff | 0365 to Liaisons | Liaison to Staff | 0365 to Staff | 0365 to Liaisons | 0365 to Staff |  | 0365 to Staff
|  |  | T minus 3 mos | T minus 8 weeks | T minus 8 weeks | T minus 4 weeks | T minus 4 weeks | T minus 2 weeks | T minus 2 weeks | T minus 1 wk | T minus 2-3 days | 4:45pm Go-Live Day | Target Go-Live | T plus 4 Days
|  | Group 1 | 2017-09-11 | 2017-10-09 |  | 2017-11-06 |  | 2017-11-20 |  | 2017-11-27 | 2017-12-01 | 2017-08-28 | 2017-12-04 | 2017-12-10
|  | Group 2 | 2017-09-18 | 2017-10-16 |  | 2017-11-13 |  | 2017-11-27 |  | 2017-12-04 | 2017-12-08 | 2017-08-28 | 2017-12-11 | 2017-12-17
|  | Group 3 | 2017-09-25 | 2017-10-23 |  | 2017-11-20 |  | 2017-12-04 |  | 2017-12-11 | 2017-12-15 | 2017-08-28 | 2017-12-18 | 2017-12-24
|  | Group 4 | 2017-10-16 | 2017-11-13 |  | 2017-12-11 |  | 2017-12-25 |  | 2018-01-01 | 2018-01-05 | 2017-08-28 | 2018-01-08 | 2018-01-14
|  | Group 5 | 2017-10-23 | 2017-11-20 |  | 2017-12-18 |  | 2018-01-01 |  | 2018-01-08 | 2018-01-12 | 2017-08-28 | 2018-01-15 | 2018-01-21
|  | Group 6 | 2017-10-30 | 2017-11-27 |  | 2017-12-25 |  | 2018-01-08 |  | 2018-01-15 | 2018-01-19 | 2017-09-11 | 2018-01-22 | 2018-01-28
|  | Group 7 | 2017-11-06 | 2017-12-04 |  | 2018-01-01 |  | 2018-01-15 |  | 2018-01-22 | 2018-01-26 | 2017-10-02 | 2018-01-29 | 2018-02-04
|  | Group 8 | 2017-11-13 | 2017-12-11 |  | 2018-01-08 |  | 2018-01-22 |  | 2018-01-29 | 2018-02-02 | 2017-10-16 | 2018-02-05 | 2018-02-11
|  | Group 9 | 2017-11-20 | 2017-12-18 |  | 2018-01-15 |  | 2018-01-29 |  | 2018-02-05 | 2018-02-09 | 2017-10-30 | 2018-02-12 | 2018-02-18
|  | Group 10 | 2017-11-27 | 2017-12-25 |  | 2018-01-22 |  | 2018-02-05 |  | 2018-02-12 | 2018-02-16 | 2017-11-06 | 2018-02-19 | 2018-02-25
|  | Group 11 | 2017-12-04 | 2018-01-01 |  | 2018-01-29 |  | 2018-02-12 |  | 2018-02-19 | 2018-02-23 | 2017-12-04 | 2018-02-26 | 2018-03-04
|  | Group 12 | 2017-12-11 | 2018-01-08 |  | 2018-02-05 |  | 2018-02-19 |  | 2018-02-26 | 2018-03-02 | 2017-12-11 | 2018-03-05 | 2018-03-11
Formulas:
Email L6 = [Target]+6